## Sheet1
Risk ID | AI RMF Function (Govern/Map/Measure/Manage) | Risk Category | Risk Description | Impact (High/Medium/Low) | Likelihood (High/Medium/Low) | Risk Rating (Impact x Likelihood) | Mitigation Strategy | Risk Owner | Status (Open/Monitoring/Mitigated/Closed) | Date Identified | Target Resolution Date | Last Review Date | Notes/Comments
GOV-001 | Govern | Governance | Lack of clear accountability for AI system risks | High | Medium | High | Assign AI Risk Officer and establish oversight committee | AI Risk Officer | Open | 2025-09-17 | 2025-12-31 | 2025-09-17
GOV-002 | Govern | Compliance | Non-compliance with emerging AI regulations (e.g., EU AI Act, DPDPA) | High | High | High | Regular legal reviews and compliance audits | Legal & Compliance | Monitoring | 2025-09-17 | 2026-03-31 | 2025-09-17
GOV-003 | Govern | Ethics | AI system decisions conflict with organizational values or ethics | High | Medium | High | Establish AI ethics principles and review board | AI Risk Committee | Open | 2025-09-17 | 2026-01-15 | 2025-09-17
GOV-004 | Govern | Resource Constraints | Insufficient skills, budget, or tools for AI risk management | Medium | High | High | Allocate dedicated AI risk resources and training | Executive Leadership | Monitoring | 2025-09-17 | 2026-02-28 | 2025-09-17
MAP-001 | Map | Data Quality | Training data contains bias or is not representative | High | High | High | Perform bias testing and diversify datasets | Data Science Lead | Open | 2025-09-17 | 2025-11-30 | 2025-09-17
MAP-002 | Map | Application Context | AI system used outside its intended scope | High | Medium | High | Define clear usage policies and monitor applications | Business Owner | Open | 2025-09-17 | 2025-12-15 | 2025-09-17
MAP-003 | Map | Sensitive Data | AI model trained on personal or regulated data without authorization | High | Medium | High | Conduct privacy impact assessments and data minimization | Privacy Officer | Open | 2025-09-17 | 2025-11-30 | 2025-09-17
MAP-004 | Map | Third-Party Dependencies | Reliance on unverified third-party data or models | Medium | Medium | Medium | Perform vendor risk assessments and audits | Procurement Lead | Monitoring | 2025-09-17 | 2025-12-31 | 2025-09-17
MEA-001 | Measure | Performance | Model underperforms on edge cases or minority groups | High | Medium | High | Expand test datasets and conduct scenario testing | QA Lead | Monitoring | 2025-09-17 | 2025-12-31 | 2025-09-17
MEA-002 | Measure | Explainability | AI system is a black box and lacks interpretability | Medium | High | High | Implement explainable AI techniques (e.g., SHAP, LIME) | AI Engineer | Open | 2025-09-17 | 2026-01-15 | 2025-09-17
MEA-003 | Measure | Fairness | AI outcomes disproportionately affect vulnerable populations | High | Medium | High | Conduct fairness audits and stakeholder consultations | Ethics Officer | Open | 2025-09-17 | 2026-02-28 | 2025-09-17
MEA-004 | Measure | Validation Gaps | Insufficient independent testing before deployment | High | Medium | High | Require third-party validation for high-risk AI systems | QA Lead | Open | 2025-09-17 | 2025-12-31 | 2025-09-17
MEA-005 | Measure | Security Testing | AI system lacks adversarial robustness testing | High | Medium | High | Introduce red-teaming and adversarial testing protocols | Security Team | Monitoring | 2025-09-17 | 2025-12-31 | 2025-09-17
MAN-001 | Manage | Model Drift | Model performance degrades due to data drift | High | High | High | Implement monitoring and retraining processes | ML Ops Lead | Open | 2025-09-17 | 2025-12-01 | 2025-09-17
MAN-002 | Manage | Security | AI system vulnerable to adversarial attacks | High | Medium | High | Conduct adversarial testing and apply defenses | Security Team | Open | 2025-09-17 | 2025-11-30 | 2025-09-17
MAN-003 | Manage | Incident Response | No defined process for AI-related failures or harms | High | Medium | High | Establish AI incident response playbooks | AI Risk Officer | Open | 2025-09-17 | 2025-12-20 | 2025-09-17
MAN-004 | Manage | Reputational Risk | Negative public perception due to AI misuse or errors | High | Medium | High | Develop communication and escalation protocols | Communications Lead | Monitoring | 2025-09-17 | 2025-12-31 | 2025-09-17
MAN-005 | Manage | Operational Dependency | Over-reliance on AI without human oversight | High | Medium | High | Enforce human-in-the-loop for critical decisions | Business Owner | Open | 2025-09-17 | 2026-01-31 | 2025-09-17
MAN-006 | Manage | Environmental Impact | High energy consumption during model training and inference | Medium | Medium | Medium | Use efficient algorithms and monitor carbon footprint | Sustainability Officer | Monitoring | 2025-09-17 | 2026-03-15 | 2025-09-17
MAN-007 | Manage | Vendor Lock-In | Difficulty switching from vendor-provided AI solutions | Medium | Medium | Medium | Develop exit strategies and open standards adoption | Procurement Lead | Monitoring | 2025-09-17 | 2026-04-30 | 2025-09-17
MAN-008 | Manage | System Integration | Integration issues with legacy systems causing disruptions | Medium | Medium | Medium | Conduct integration testing and phased rollouts | IT Ops Lead | Open | 2025-09-17 | 2026-01-15 | 2025-09-17
MAN-009 | Manage | Continuous Monitoring | Inadequate post-deployment monitoring for risks | High | High | High | Deploy automated monitoring dashboards | ML Ops Lead | Open | 2025-09-17 | 2025-12-10 | 2025-09-17