## 🏠 Dashboard
CUSTOMER ONBOARDING TRACKER ¦ Compliance Automation Platform
Complete all [placeholder] fields before sharing with the customer
CUSTOMER INFORMATION | [6 empty] | ONBOARDING CONTACTS
Customer Name | [Customer Organization] | [5 empty] | Customer Champion | [Name — Title — Email]
Target Framework(s) | [SOC 2 / ISO 27001 / HIPAA / etc.] | [5 empty] | Technical Lead | [Name — Title — Email]
Subscription Tier | [Starter / Growth / Enterprise] | [5 empty] | Exec Sponsor | [Name — Title — Email]
Onboarding Start | [DD-MMM-YYYY] | [5 empty] | CSM (Platform) | [Name — Email]
Target Go-Live | [DD-MMM-YYYY] | [5 empty] | Solutions Engineer | [Name — Email]
Contract End Date | [DD-MMM-YYYY] | [5 empty] | Support Alias | [support@platform.com]
PHASE PROGRESS SUMMARY
Phase | Name | Duration | Total Tasks | Complete | In Progress | Not Started | Completion % | Status
Phase 1 | Kickoff & Discovery | Week 1–2 | 7 | 0 | 0 | 7 | 0% | ⬜ Not Started
Phase 2 | Platform Setup & Integration | Week 3–5 | 8 | 0 | 0 | 8 | 0% | ⬜ Not Started
Phase 3 | Control Implementation & Training | Week 6–9 | 8 | 0 | 0 | 8 | 0% | ⬜ Not Started
Phase 4 | Audit Readiness & Handover | Week 10–12 | 8 | 0 | 0 | 8 | 0% | ⬜ Not Started
OVERALL ONBOARDING COMPLETION |  |  | 31 | 0 | 0 | 31 | 0% | ⚠️ Needs Attention
KEY MILESTONES
# | Milestone | Target Date | Actual Date | Owner | Status | Notes
M1 | Kickoff call completed & onboarding plan signed | [Week 1] |  | [CSM] | ⬜ Not Started
M2 | Platform tenant provisioned & SSO configured | [Week 2] |  | [SE] | ⬜ Not Started
M3 | All integrations live & evidence collection active | [Week 5] |  | [SE] | ⬜ Not Started
M4 | 100% controls mapped with owners assigned | [Week 7] |  | [Champion] | ⬜ Not Started
M5 | Employee training >90% completion | [Week 9] |  | [CSM] | ⬜ Not Started
M6 | Audit-ready evidence package compiled | [Week 11] |  | [CSM] | ⬜ Not Started
M7 | Auditor portal configured & read-only access shared | [Week 11] |  | [SE] | ⬜ Not Started
M8 | Go-live sign-off received from customer | [Week 12] |  | [CSM] | ⬜ Not Started

## 📋 Phase 1
PHASE 1 — Kickoff & Discovery ¦ Week 1–2
# | Activity / Task | Category | Owner | Start Week | End Week | Status | Priority | Notes / Blockers | Evidence / Artifact | Completion %
1.1 | Executive kickoff call — align on goals, timelines, success metrics | Kickoff | [CSM] | 1 | 1 | ⬜ Not Started | 🔴 High |  | [Meeting notes, signed onboarding plan] | 0%
1.2 | Technical discovery session — inventory tech stack & integration readiness | Discovery | [SE] | 1 | 1 | ⬜ Not Started | 🔴 High |  | [Tech stack inventory sheet] | 0%
1.3 | Identify & confirm compliance champion, tech owner, executive sponsor | Stakeholders | [CSM] | 1 | 1 | ⬜ Not Started | 🔴 High |  | [RACI sign-off email] | 0%
1.4 | Provision platform tenant — configure SSO and initial user roles | Setup | [SE] | 1 | 2 | ⬜ Not Started | 🔴 High |  | [Tenant URL + admin credentials] | 0%
1.5 | Send onboarding checklist and assign workstream owners | Admin | [CSM] | 1 | 1 | ⬜ Not Started | 🟡 Medium |  | [Checklist shared via email/Slack] | 0%
1.6 | Initial gap assessment walkthrough — review current compliance posture | Assessment | [CSM + SE] | 2 | 2 | ⬜ Not Started | 🔴 High |  | [Gap assessment report] | 0%
1.7 | Share this onboarding tracker with customer champion for alignment | Admin | [CSM] | 2 | 2 | ⬜ Not Started | 🟡 Medium |  | [Shared tracker link / email] | 0%
PHASE TOTALS — 7 Tasks | [5 empty] | 0 Complete | 5 High Priority |  |  | 0%

## 📋 Phase 2
PHASE 2 — Platform Setup & Integration ¦ Week 3–5
# | Activity / Task | Category | Owner | Start Week | End Week | Status | Priority | Notes / Blockers | Evidence / Artifact | Completion %
2.1 | Connect cloud integration — AWS / GCP / Azure (auto-evidence collection) | Integration | [SE] | 3 | 3 | ⬜ Not Started | 🔴 High |  | [Integration status screenshot] | 0%
2.2 | Configure IdP integration (Okta / Azure AD / Google Workspace) | Integration | [SE + Tech Lead] | 3 | 4 | ⬜ Not Started | 🔴 High |  | [IdP connection confirmed] | 0%
2.3 | Set up MDM connector (Jamf / Intune / Kandji) for endpoint compliance | Integration | [SE + Tech Lead] | 3 | 4 | ⬜ Not Started | 🟡 Medium |  | [MDM sync active] | 0%
2.4 | Connect HRMS / People Ops tool for employee training sync | Integration | [SE + Tech Lead] | 4 | 4 | ⬜ Not Started | 🟡 Medium |  | [HRMS sync confirmed, employee list imported] | 0%
2.5 | Import & map organizational structure (departments, teams, roles) | Configuration | [Champion] | 4 | 5 | ⬜ Not Started | 🟡 Medium |  | [Org chart in platform] | 0%
2.6 | Configure framework scope — select applicable controls for target framework | Configuration | [Champion + SE] | 4 | 5 | ⬜ Not Started | 🔴 High |  | [Scope document signed off] | 0%
2.7 | Upload existing policies; run AI-assisted policy gap analysis | Policy | [Champion] | 5 | 5 | ⬜ Not Started | 🔴 High |  | [Policies uploaded, gap report reviewed] | 0%
2.8 | Configure evidence collection schedules and data retention settings | Configuration | [SE] | 5 | 5 | ⬜ Not Started | 🟡 Medium |  | [Collection schedule configured] | 0%
PHASE TOTALS — 8 Tasks | [5 empty] | 0 Complete | 4 High Priority |  |  | 0%

## 📋 Phase 3
PHASE 3 — Control Implementation & Training ¦ Week 6–9
# | Activity / Task | Category | Owner | Start Week | End Week | Status | Priority | Notes / Blockers | Evidence / Artifact | Completion %
3.1 | Control mapping — assign each in-scope control to an owner | Controls | [Champion] | 6 | 7 | ⬜ Not Started | 🔴 High |  | [Control ownership matrix] | 0%
3.2 | Validate auto-evidence collection is working for each control | Controls | [SE + Champion] | 6 | 7 | ⬜ Not Started | 🔴 High |  | [Evidence collection audit log] | 0%
3.3 | Policy acknowledgment campaign — launch employee sign-off workflows | Policy | [Champion] | 7 | 8 | ⬜ Not Started | 🔴 High |  | [Acknowledgment completion report] | 0%
3.4 | Security awareness training — assign, launch, and track completion | Training | [CSM + Champion] | 7 | 9 | ⬜ Not Started | 🔴 High |  | [Training completion report >90%] | 0%
3.5 | Vendor / TPRM — import vendor list and send risk assessments | TPRM | [Champion] | 8 | 9 | ⬜ Not Started | 🟡 Medium |  | [Vendor assessments sent & tracked] | 0%
3.6 | Risk register setup — document risks, likelihood, impact, treatment plans | Risk | [Champion] | 8 | 9 | ⬜ Not Started | 🔴 High |  | [Risk register populated & reviewed] | 0%
3.7 | Internal audit readiness walkthrough — identify and assign evidence gaps | Audit | [CSM + Champion] | 9 | 9 | ⬜ Not Started | 🔴 High |  | [Gap list with owner & due date] | 0%
3.8 | Close all open evidence gaps from internal walkthrough | Audit | [Champion] | 9 | 9 | ⬜ Not Started | 🟡 Medium |  | [All gaps resolved or risk-accepted] | 0%
PHASE TOTALS — 8 Tasks | [5 empty] | 0 Complete | 6 High Priority |  |  | 0%

## 📋 Phase 4
PHASE 4 — Audit Readiness & Handover ¦ Week 10–12
# | Activity / Task | Category | Owner | Start Week | End Week | Status | Priority | Notes / Blockers | Evidence / Artifact | Completion %
4.1 | Generate full compliance readiness report — review platform trust score | Audit | [CSM + Champion] | 10 | 10 | ⬜ Not Started | 🔴 High |  | [Readiness report (>85% score)] | 0%
4.2 | Configure auditor portal — set up read-only auditor access | Audit | [SE] | 10 | 10 | ⬜ Not Started | 🔴 High |  | [Auditor login confirmed] | 0%
4.3 | Export evidence package — compile complete audit artifact bundle | Audit | [Champion] | 10 | 11 | ⬜ Not Started | 🔴 High |  | [Evidence bundle ZIP / folder link] | 0%
4.4 | Review and close all open exceptions and remediation items | Audit | [Champion] | 11 | 11 | ⬜ Not Started | 🔴 High |  | [Exceptions log — all resolved/accepted] | 0%
4.5 | Customer admin training — platform admin, user management, reporting | Training | [SE + CSM] | 11 | 12 | ⬜ Not Started | 🟡 Medium |  | [Training recording + user guide] | 0%
4.6 | Introduce ongoing success model — QBR cadence, support channels, SLAs | Handover | [CSM] | 12 | 12 | ⬜ Not Started | 🟡 Medium |  | [Ongoing success playbook shared] | 0%
4.7 | Formal go-live sign-off — customer signature on onboarding completion | Handover | [CSM + Champion] | 12 | 12 | ⬜ Not Started | 🔴 High |  | [Signed go-live acceptance form] | 0%
4.8 | Transition to steady-state success — hand off to ongoing CSM rhythm | Handover | [CSM] | 12 | 12 | ⬜ Not Started | 🟡 Medium |  | [First QBR date scheduled] | 0%
PHASE TOTALS — 8 Tasks | [5 empty] | 0 Complete | 5 High Priority |  |  | 0%

## 👥 RACI
RACI MATRIX — Roles & Responsibilities
R | Responsible | A | Accountable | C | Consulted | I | Informed
# | Activity | Phase | CSM | Solutions Engineer | Customer Champion | Tech Lead | Exec Sponsor | Notes
1 | Executive kickoff call | Phase 1 | R/A | C | R | C | I | Champion attends; Exec reviews output
2 | Tenant provisioning & SSO | Phase 1 | A | R | I | C | I | SE leads; champion provides IdP details
3 | Tech stack discovery & integration map | Phase 1 | C | R/A | C | R | I | Tech lead provides credentials
4 | Cloud integration setup | Phase 2 | I | R/A | C | R | I | IAM roles needed from customer cloud
5 | IdP & HRMS integration | Phase 2 | I | R/A | C | R | I | IdP admin access from customer IT
6 | Framework scope definition | Phase 2 | C | C | R/A | C | I | Champion owns scope sign-off
7 | Policy upload & gap analysis | Phase 2 | C | R | R/A | I | I | Champion provides existing policies
8 | Control ownership assignment | Phase 3 | A | I | R | C | I | Champion assigns to dept owners
9 | Evidence collection validation | Phase 3 | C | R/A | I | R | I | SE verifies; tech lead checks gaps
10 | Policy acknowledgment campaign | Phase 3 | A | I | R | C | I | HR/Ops team coordinates internally
11 | Employee security training | Phase 3 | A | I | R | C | I | Target: >90% completion by Week 9
12 | Vendor risk assessments (TPRM) | Phase 3 | A | I | R | I | I | Champion owns vendor relationship list
13 | Risk register population | Phase 3 | C | I | R/A | I | C | Exec consulted for strategic risks
14 | Auditor portal configuration | Phase 4 | C | R/A | C | I | I | Auditor firm must be identified first
15 | Evidence package compilation | Phase 4 | A | C | R | C | I | Champion owns final artifact bundle
16 | Customer admin training | Phase 4 | A | R | C | R | I | SE leads; champion + tech lead attend
17 | Go-live sign-off | Phase 4 | A | C | R | C | R | Executive sponsor approves go-live

## 📊 KPIs & Metrics
SUCCESS METRICS & HEALTH INDICATORS
# | Metric | Category | Target | Measure By | Actual Value | Status | Trend | Owner | Notes
K1 | Platform login — minimum 3 unique users | Adoption | By end Week 1 | Week 1 |  | ⬜ |  | [CSM]
K2 | Integration connections active | Integration | 100% of mapped tools | Week 5 |  | ⬜ |  | [SE]
K3 | Auto-evidence collection rate | Evidence | >80% automated | Week 8 |  | ⬜ |  | [SE]
K4 | Controls mapped to owners | Controls | 100% in-scope controls | Week 7 |  | ⬜ |  | [Champion]
K5 | Policy acknowledgment rate (employees) | Policy | >90% employee sign-off | Week 9 |  | ⬜ |  | [CSM]
K6 | Security awareness training completion | Training | >95% employees | Week 9 |  | ⬜ |  | [CSM]
K7 | Vendor assessments sent (Tier 1 vendors) | TPRM | 100% Tier 1 vendors | Week 10 |  | ⬜ |  | [Champion]
K8 | Open risk items in risk register | Risk | <10 open / high risks | Week 9 |  | ⬜ |  | [Champion]
K9 | Platform trust score / audit readiness % | Audit | >85% readiness score | Week 12 |  | ⬜ |  | [CSM]
K10 | Time-to-first-audit from go-live | Audit | <90 days from go-live | Post go-live |  | ⬜ |  | [CSM]
K11 | Customer NPS / onboarding satisfaction score | Experience | >8 / 10 | Week 12 |  | ⬜ |  | [CSM]

## ⚠️ Risk Register
ONBOARDING RISK REGISTER
ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Action | Owner | Status | Resolution / Notes
R01 | Delayed integration credentials from customer IT team | Technical | Medium | High | 6 | Request credentials at kickoff call; SE to escalate if not received by Day 5 | [SE] | Open
R02 | Low employee training / policy acknowledgment completion | People | Medium | Medium | 4 | Weekly reminder cadence; CSM to engage HR/Ops champion directly | [CSM] | Open
R03 | Scope creep — additional frameworks added mid-onboarding | Scope | Low | High | 3 | Formal change request process; any scope additions require addendum & revised timeline | [CSM + AE] | Open
R04 | Key customer champion leaves during onboarding | Stakeholder | Low | High | 3 | Multi-thread all relationships; document all key decisions and commitments | [CSM] | Open
R05 | Audit date pulled forward by customer | Timeline | Low | High | 3 | Maintain 2-week buffer in plan; prioritize Tier 1 evidence and critical controls | [CSM] | Open
R06 | Platform integration failure (API breaking change) | Technical | Low | High | 3 | SE monitors integration health daily during Phase 2; escalate to engineering if needed | [SE] | Open
R07 | Evidence gaps not resolved before audit | Compliance | Medium | High | 6 | Weekly evidence gap review from Week 6; assign each gap a due date and owner | [Champion] | Open
R08 | Vendor assessments not returned by Tier 1 vendors | TPRM | Medium | Medium | 4 | Send reminders at 5, 10, 15 days; risk-accept with justification if no response | [Champion] | Open

## 💬 Comms Log
COMMUNICATION LOG & MEETING TRACKER
Date | Meeting / Touchpoint | Type | Attendees | Key Decisions | Action Items | Owner | Due Date
[Week 1] | Executive Kickoff Call | Kickoff | [CSM + SE + Champion + Exec] | [Align on goals, timeline, success metrics] | [Share onboarding tracker; send integration checklist] | [CSM] | [Week 1]
[Week 1] | Technical Discovery Session | Technical Check-in | [SE + Tech Lead] | [Map tech stack, identify integration owners] | [Request cloud IAM credentials and IdP details] | [SE] | [Week 1]
[Week 2] | Onboarding Weekly Sync #1 | Weekly Sync | [CSM + Champion] | [Review kickoff actions, confirm tenant provisioning] | [Close gap assessment; assign control owners] | [CSM] | [Week 2]
[Week 3] | Onboarding Weekly Sync #2 | Weekly Sync | [CSM + Champion] |  |  | [CSM] | [Week 3]
[Week 4] | Onboarding Weekly Sync #3 | Weekly Sync | [CSM + Champion] |  |  | [CSM] | [Week 4]
[Week 5] | Integration Health Check | Technical Check-in | [SE + Tech Lead] |  |  | [SE] | [Week 5]
[Week 6] | Onboarding Weekly Sync #4 | Weekly Sync | [CSM + Champion] |  |  | [CSM] | [Week 6]
[Week 8] | Monthly Executive Update #1 | Exec Update | [CSM + Exec Sponsor] |  |  | [CSM] | [Week 8]
[Week 9] | Internal Audit Readiness Review | Weekly Sync | [CSM + SE + Champion] |  |  | [CSM] | [Week 9]
[Week 10] | Audit Package Review | Technical Check-in | [SE + Champion] |  |  | [SE] | [Week 10]
[Week 12] | Go-Live Review & Sign-Off | Weekly Sync | [CSM + Champion + Exec] |  |  | [CSM] | [Week 12]