## Sheet1
ISMS Implementation Project
Project Title | {Project's title} |  | Company Name | {Company's Name}
Project Manager | {PM's Name} |  | Date | {mm/dd/yy}
WBS NUMBER | TASK TITLE | Responsible Party | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
1 | Project Introduction
1.1 | Initiate ISMS Project | Project Manager |  |  |  | 100%
1.1.1 | Conduct Management Awareness Session | ISO Consultant |  |  |  | 100%
1.2 | Secure Management Commitment | Project Manager |  |  |  | 90%
1.3 | Understand Organization Context | ISO Consultant |  |  |  | 40%
1.4 | Define ISMS Scope | Project Manager, Consultant |  |  |  | 70%
2 | Execution
2.1 | Conduct Gap Assessment | ISO Consultant |  |  |  | 22%
2.2 | Develop Risk Management Process | ISO Consultant |  |  |  | 16%
2.3 | Conduct Risk Assessment | Project Manager, Consultant |  |  |  | 0%
2.4 | Develop Statement of Applicability | ISO Consultant |  |  |  | 0%
3 | Implementation
3.1 | Develop Information Security Policies | Project Manager, Consultant |  |  |  | 0%
3.2 | Develop Supporting Procedures | Project Manager, Consultant |  |  |  | 0%
3.2.1 | Implement Selected Controls | IT Department |  |  |  | 0%
3.2.2 | Conduct Awareness and Training Programs | HR Department, Consultant |  |  |  | 0%
4 | Monitoring
4.1 | Monitor and Measure ISMS Performance | IT Department, Consultant |  |  |  | 0%
4.2 | Conduct Internal Audits | Internal Audit Team |  |  |  | 0%
4.3 | Conduct Management Review | Project Manager, Consultant |  |  |  | 0%
4.4 | Treat Nonconformities | Project Manager, Consultant |  |  |  | 0%
4.5 | Implement Continual improvement | Project Manager
4.6 | Prepare for Certification Audit | Auditor